## 用户要求生成Excel表格
ID | User Story | Acceptance Criteria | Priority | Estimation | Iteration Planning
US-01 | User Registration with Role Selection: As a new user, I want to register for an account by providing my details and selecting my role (TA/MO/Admin), so that I can access the appropriate features of the system. | 1. Registration form includes: name, email, password, confirm password, role dropdown, skills (optional)2. Email must be unique and in valid format3. Password minimum 6 characters with confirmation match4. Role selection required with three options: TA, MO, Admin5. Skills field accepts multi-line text input6. Successful registration redirects to login page with success message7. Duplicate email shows error message8. All fields validated on both client and server side | Must Have | 5 | Iteration 1
US-02 | User Login with Role-Based Redirection: As a registered user, I want to log in with my email and password, so that I can access my role-specific dashboard. | 1. Login form with email and password fields2. Credentials validated against stored user data3. Successful login creates user session4. Users redirected to role-specific dashboard (TA/MO/Admin)5. Failed login displays error message6. Email value retained on failed attempt7. Session timeout set to 30 minutes8. Unauthorized access redirects to login | Must Have | 3 | Iteration 1
US-03 | Secure Logout: As a logged-in user, I want to securely log out of the system, so that my account remains protected. | 1. Logout link visible in navigation bar on all pages2. Clicking logout clears user session3. User redirected to login page after logout4. Success message displayed after logout5. Back button cannot access protected pages after logout | Must Have | 2 | Iteration 2
US-04 | TA Profile Information Management: As a TA, I want to view and update my profile information including name, email, and skills, so that I can keep my details current. | 1. Profile page accessible from TA navigation menu2. Displays current: name, email, role, skills3. Name and email fields editable4. Role field read-only with visual indication5. Skills field multi-line text area6. Save button updates user data7. Success message shown after save8. Session updated with new information9. Email uniqueness validated10. Invalid email format rejected | Must Have | 5 | Iteration 2
US-05 | Resume File Upload: As a TA, I want to upload my resume in PDF or Word format, so that MOs can review my detailed qualifications. | 1. Upload section in profile page2. Supported formats: PDF (.pdf), Word (.doc, .docx)3. Maximum file size: 5MB4. Current resume link displayed if exists5. File selector provided6. Upload triggered on form submission7. Files stored in designated server directory8. Filename format: {userId}_{timestamp}.{extension}9. User record updated with file path10. Success message after upload11. Format validation with error message12. Size validation with error message13. New upload replaces previous file | Must Have | 8 | Iteration 2
US-06 | Resume Download Verification: As a TA, I want to download my uploaded resume, so that I can verify the file is correct. | 1. "View Resume" link shown in profile page2. Link opens file in new tab or downloads3. "Not uploaded" message shown if no resume4. Resume link also shown in applications page5. Server validates user can only access own resume6. 404 error shown if file missing | Should Have | 3 | Iteration 2
US-07 | Browse Open Positions: As a TA, I want to browse all available open positions, so that I can find opportunities matching my interests. | 1. "Browse Positions" link in TA navigation2. Page displays all positions with status OPEN3. Each position card shows: title, description, requirements, hours/week, status badge4. Status badges color-coded: OPEN (green), CLOSED (gray)5. Already applied positions show "Applied" button (disabled)6. Not applied positions show "Apply for Position" button (enabled)7. Empty state message if no open positions8. Positions sorted by creation date (newest first)9. "Return to Dashboard" button at bottom | Must Have | 5 | Iteration 2
US-08 | Submit Job Application: As a TA, I want to apply for a position by clicking an apply button, so that the system records my application with timestamp and pending status. | 1. "Apply for Position" button shows confirmation dialog2. Confirmation required before submission3. System creates application record with: ID, TA ID, position ID, status (PENDING), timestamp4. Application saved to data storage5. Duplicate application prevention (same TA + position)6. Duplicate attempt shows error message7. Success message displayed after application8. Button changes to "Applied" (disabled)9. Application visible in "My Applications" page10. CLOSED positions cannot be applied to | Must Have | 8 | Iteration 2
US-09 | Track Application Status: As a TA, I want to view all my applications with their current status, so that I can track my application progress. | 1. "My Applications" link in TA navigation2. Page displays all applications for current TA3. Each application card shows: position details, application date, status, resume status4. Status badges color-coded: PENDING (orange), SELECTED (green), REJECTED (red), WITHDRAWN (gray)5. Resume uploaded: "Download Resume" button shown6. Resume not uploaded: "Not Uploaded" message with "Upload" link7. PENDING status: "Withdraw Application" button shown8. SELECTED status: Congratulations message shown9. REJECTED status: Regret message shown10. WITHDRAWN status: Withdrawal confirmation shown11. Empty state with "Browse Positions" link if no applications12. Applications sorted by date (newest first) | Must Have | 8 | Iteration 2
US-10 | Withdraw Pending Application: As a TA, I want to withdraw my pending application, so that I can cancel if my circumstances change. | 1. "Withdraw Application" button shown for PENDING applications2. Confirmation dialog displayed on click3. User must confirm withdrawal action4. Application status updated from PENDING to WITHDRAWN5. Data storage updated6. Success message displayed7. Page refreshes showing withdrawal message8. Only PENDING applications can be withdrawn9. Other statuses do not show withdraw button10. Withdrawn applications remain in list | Should Have | 5 | Iteration 2
US-11 | Create New Position: As an MO, I want to create a new TA position by filling in details, so that I can recruit suitable candidates. | 1. "Create Position" link in MO navigation2. Form includes: title (required, max 200 chars), description (required, multi-line), requirements (optional, multi-line), hours/week (required, 1-40)3. "Create Position" and "Cancel" buttons provided4. All required fields validated5. System auto-generates position ID6. System auto-sets creator to current MO user ID7. System auto-sets status to OPEN8. Position saved to data storage9. Success redirects to "My Positions" page10. Success message displayed11. Validation errors shown with form data retained12. Hours must be between 1-40 | Must Have | 8 | Iteration 3
US-12 | View Created Positions: As an MO, I want to view all positions I have created, so that I can manage my recruitment activities. | 1. "My Positions" link in MO navigation2. Page displays all positions created by current MO3. Each position card shows: title, status badge, ID, description, requirements, hours/week4. "View Applications" and "Delete Position" buttons on each card5. Empty state with "Create First Position" button if no positions6. Positions sorted by creation date (newest first)7. Status badges: OPEN (green), CLOSED (gray) | Must Have | 5 | Iteration 3
US-13 | Delete Position: As an MO, I want to delete a position, so that I can cancel recruitment that is no longer needed. | 1. "Delete Position" button shown on each position card2. Confirmation dialog displayed on click3. User must confirm deletion4. Position record deleted from storage5. All applications for position also deleted (cascade)6. Success message displayed7. Page refreshes with position removed8. Only position creator can delete9. Error message if position not found | Should Have | 5 | Iteration 3
US-14 | Review Position Applications: As an MO, I want to view all applications for a specific position, so that I can evaluate and compare candidates. | 1. "View Applications" button on position cards2. Redirects to applications page for that position3. Position details card shown at top: title, ID, description, hours4. All applications for position displayed5. Each application card shows: applicant name, status badge, application ID, email, skills, resume link6. Status badges: PENDING (orange), SELECTED (green), REJECTED (red)7. PENDING applications (when no one selected): "Select This Applicant" button shown8. SELECTED applications: "✓ Selected" indicator shown9. If someone already selected: other PENDING applications hide select button10. Empty state message if no applications11. "Return to My Positions" button at bottom12. Applications sorted by submission date (newest first) | Must Have | 8 | Iteration 3
US-15 | Select Applicant with Auto-Rejection: As an MO, I want to select one applicant for a position with the system automatically rejecting other pending applications, so that the process is efficient. | 1. "Select This Applicant" button shown for PENDING applications2. Confirmation dialog displayed on click3. User must confirm selection4. Selected application status updated from PENDING to SELECTED5. All other PENDING applications for same position updated to REJECTED (batch operation)6. Data storage updated7. Success message displayed8. Page refreshes showing selection9. Selected application shows "✓ Selected" indicator10. Other applications show REJECTED status11. One position can only have one selected applicant12. Once selected, cannot select another13. Only position creator can select applicants | Must Have | 8 | Iteration 3
US-16 | Download Applicant Resume: As an MO, I want to download applicant resumes, so that I can thoroughly evaluate candidates. | 1. "Download Resume" button shown in application cards2. Click downloads or opens file in new tab3. "Not Uploaded" message shown if no resume4. Server validates MO has permission to view resume5. 404 error if file not found | Must Have | 3 | Iteration 3
US-17 | View TA Workload Report: As an Admin, I want to view workload statistics for all TAs, so that I can assess resource allocation and identify overworked or underutilized TAs. | 1. "Workload Report" link in Admin navigation2. Page displays all TAs in system3. Table format with columns: Number, Name, Email, Total Hours4. Total Hours = sum of hours from all SELECTED applications5. Sorted by total hours (descending - highest first)6. Empty state message if no data7. "Return to Dashboard" button at bottom | Should Have | 8 | Iteration 3
US-18 | AI Skill Matching: As a TA, I want to see how well my skills match a position via AI analysis, so that I can apply for suitable roles. | 1. System compares TA skills with requirements. 2. Display "Match Score" with brief explanation. 3. User can manually override or edit skills if AI logic is incorrect. | Could Have | 8 | Iteration 4
US-19 | AI Resume Summary: As an MO, I want to view an AI-generated summary of a resume, so that I can assess qualifications quickly. | 1. Extracts key experience from PDF/Word. 2. Must display "AI-generated - please verify" disclaimer. 3. Summary link points to source text in resume to avoid hallucination. | Could Have | 13 | Iteration 4
US-20 | AI Job Description Assistant: As an MO, I want the system to suggest requirements using AI, so that I can create posts efficiently. | 1. "Suggest Requirements" button in form. 2. AI output must be reviewed and confirmed by MO before saving (no blind acceptance). 3. MO can modify AI-suggested text. | Could Have | 8 | Iteration 4